## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
7Co5HTpOC0aUCk4wzUe_q8gAB1OU | Requirement Gathering | To do | Not started | Medium | ZAINUL AMEER ZAQUAN BIN MOHAMED ZAINI;MUHAMMAD NAUHFHAL FAWWAZ BIN MD NAZRI;MUHAMMAD HAZIQ DANIAL BIN HASAN;ALIF ISKANDAR BIN ZAMRI;AHMAD DANISH BIN JURIA @ ZAKARIA | AHMAD DANISH BIN JURIA @ ZAKARIA | 10/27/2025 |  | 10/29/2025 | false | false
HrqPYBCzxEWPPdgzgWY73MgAJE08 | Report & Presentation | To do | Not started | Medium | ZAINUL AMEER ZAQUAN BIN MOHAMED ZAINI;MUHAMMAD NAUHFHAL FAWWAZ BIN MD NAZRI;MUHAMMAD HAZIQ DANIAL BIN HASAN;ALIF ISKANDAR BIN ZAMRI;AHMAD DANISH BIN JURIA @ ZAKARIA | ALIF ISKANDAR BIN ZAMRI | 10/27/2025 |  | 12/13/2025 | false | false
fQaYQf_DlE6Izw4R4vcIQcgAJ2po | Model Training | To do | Not started | Medium | ZAINUL AMEER ZAQUAN BIN MOHAMED ZAINI;MUHAMMAD NAUHFHAL FAWWAZ BIN MD NAZRI;ALIF ISKANDAR BIN ZAMRI | ALIF ISKANDAR BIN ZAMRI | 10/27/2025 |  | 11/15/2025 | false | false
mOLYQ2Nda0i7Lk3upmpsCsgAAw4I | Model Evaluation | To do | Not started | Medium | ZAINUL AMEER ZAQUAN BIN MOHAMED ZAINI;MUHAMMAD NAUHFHAL FAWWAZ BIN MD NAZRI;ALIF ISKANDAR BIN ZAMRI | ALIF ISKANDAR BIN ZAMRI | 10/27/2025 |  | 11/21/2025 | false | false
wFHWJ1sWxk6YeHysc4xy9sgALln8 | Model Design | To do | Not started | Medium | ZAINUL AMEER ZAQUAN BIN MOHAMED ZAINI;MUHAMMAD NAUHFHAL FAWWAZ BIN MD NAZRI;ALIF ISKANDAR BIN ZAMRI | ALIF ISKANDAR BIN ZAMRI | 10/27/2025 |  | 11/08/2025 | false | false
x7pM-nEuUEu1oMlp4vK-usgABB5R | Dashboard Development | To do | Not started | Medium | MUHAMMAD HAZIQ DANIAL BIN HASAN;ALIF ISKANDAR BIN ZAMRI;AHMAD DANISH BIN JURIA @ ZAKARIA | ALIF ISKANDAR BIN ZAMRI | 10/27/2025 |  | 11/28/2025 | false | false
f1BlBAjNm0C1CpPcJUOgjsgAPpYl | Model Evaluation | To do | Completed | Medium | ZAINUL AMEER ZAQUAN BIN MOHAMED ZAINI;MUHAMMAD NAUHFHAL FAWWAZ BIN MD NAZRI;ALIF ISKANDAR BIN ZAMRI | ALIF ISKANDAR BIN ZAMRI | 10/27/2025 |  | 11/21/2025 | false | false | 10/27/2025 | ALIF ISKANDAR BIN ZAMRI
0y-VxL7h8UuFsyGLy7Ib28gAH2F2 | Testing & Validation | To do | Not started | Medium | MUHAMMAD NAUHFHAL FAWWAZ BIN MD NAZRI;MUHAMMAD HAZIQ DANIAL BIN HASAN;AHMAD DANISH BIN JURIA @ ZAKARIA | ALIF ISKANDAR BIN ZAMRI | 10/27/2025 |  | 12/05/2025 | false | false
nqVSjpJypkOIYt3UhW3HmMgABr1o | Data Collection | To do | Not started | Medium | MUHAMMAD HAZIQ DANIAL BIN HASAN;AHMAD DANISH BIN JURIA @ ZAKARIA | ALIF ISKANDAR BIN ZAMRI | 10/27/2025 |  | 11/03/2025 | false | false

## Plan name
Plan name | Smart Tracking System
Plan ID | rzkEheAUGUeRwCnDK2O0qcgAD3NK
Date of export | 10/28/2025